## Slide 1
P1A: 22 Mar 2019
Project Name: Tokio Marine OnePortal PM : Kannan
Kick Off
Design Sign Off
Requirements Sign Off
SIT Completion
Development Completion
UAT Sign Off
8 Aug 2018
Go Live
Planned Key Milestones (Phase-1A)
Overall Project Status as of 1 Apr 2019
Reporting Period : 25 Mar 2019 To 1 Apr 2019
Customer Sentiment
Allocated man-days: 1192 Planned Man-days: 2800
Utilized Man-days: 674
Team Members:.
Mourou 2. Deepti
3. Saumya 4. Kannan
Ramesh 6.
Update on main achievements / events of last week | Project Milestones/Phases & Delivery Date |  |  |  |  |  | 
UAT Completed Initial Data load completed in Production Delta Sync process deployed in production Customer Portal Application Deployed in Production | Deliverables |  |  | Due Date |  | % | Status/Remark
 | Requirements |  | P1A | 21-Sep-18 10-Oct-18 |  | 100 | Completed
 | Design |  | P1A | 28-Sep-18 12-Oct-18 26-Oct-18 |  | 100 | Completed
 | Development |  | P1A | 31-Dec-18 |  | 100 | Completed
Planned achievements / Activities for this / next week | SIT |  | P1A | 24-Jan-19 |  | 100 | Completed
Fixing VAPT Issues 4 Issues identified during live verification Phase 1b requirement meeting | UAT Completion |  | P1A | 08-Mar-19 |  | 100 | Completed
 | Go-live |  | P1A | 15-Mar-19 |  | 100 | Completed
Issues (I) / Risks (R) / Escalations (E) to be dealt with | Overall Progress |  |  |  |  |  | 
Overall project under estimated and will have major cost impact. Quality issues in Trigyn deliverables | Phases | Progress % |  |  | Due Date |  | Remarks
 | Phase 1 | 50 |  |  | 9-May-19 |  | Tentative
 | Phase 2 | - |  |  | 11-Jul-19 |  | Tentative
 | Phase 3 | - |  |  | 30-Sep-19 |  | Tentative
 | Warranty | - |  |  | 29-Nov-19 |  | 2 Months
P1A: 21 Sep 2018
P1A: 28 Sep 2018
P1A: 31 Dec 2018
P1A:24 Jan 2019
P1A: 27 Mar 2019